Covid in Jails- Redcap Data Cleaning

Week of 10-19-2020


2020-11-10

Table of Contents


## Project Enrollments

|  |  |  |  |
| --- | --- | --- | --- |
| Population | Weekly Enrollments | Follow ups | Total Enrolled |
| incarcerated | 24 | 1 | 216 |
| staff | 4 | 4 | 196 |
| test | 0 | 0 | 6 |

### Enrollment over time



## Warning: Removed 20 rows containing non-finite values (stat\_count).



## Accomplishments for the week

* second full week of testing
* With wifi - > no probblems with Redcap

## Challenges

* Running low on premier tests and purple lid tubes

## Quality Control Issues

|  |  |  |  |
| --- | --- | --- | --- |
| population | Resolved QC Issues | Open QC Issues | QC Issues for Discussion |
| incarcerated | 0 | 46 | 1 |
| staff | 13 | 87 | 0 |

### Types of QC Issues

The QC issues we have are as follows

##### Issues for Discussion Amongst the team

## [1] "This person had tested positive for Covid in June and also recently in September but was asymptomatic and was negative for antibodies"

##### Other QC Issues

|  |  |
| --- | --- |
| qc\_notes | n |
| Consent date is wrong | 1 |
| Missing consent confirmation signature | 103 |
| Missing consent signature | 29 |
| Need to delete 6 end followups | 1 |